## Example Crit Factor Spreadsheet
Product: Quality Audit
Feature/ | Critical Factors
Component | Supplier Dependent | Computer Failure | Consultant Availability | Production Capacity | Long Lead Time | Confidentiality | Custom Work
List of questions |  |  | ✔ |  | ✔ |  | ✔
Data collection form | ✔ |  |  | ✔
Survey tabulations |  | ✔ |  |  |  | ✔
Analysis report |  |  | ✔ | ✔ |  |  | ✔
Recommendations |  |  | ✔ | ✔ |  |  | ✔
Organization Responsible for Factor
Industry consultants |  |  |  |  | O | O | O
Quality consultants |  |  | O |  | O | O | O
Office operations | O | O |  | O | O | O | O
| ✔ | Critial Fator for Feature/Component
| O | Organization with responsibility for factor in at least one checked component

## Example Org Counter Measures
Identify specific countermeasures below for by each organizational unit for each affected critical factor-component.
Organizational Unit: | Industry Consultants
Component | Critical Factor | Countermeasure(s)
List of questions | Long Lead Time
List of questions | Custom Work
Survey Tabulations | Confidentiality
Analysis Report | Custom Work
Recommendations | Custom Work
Organizational Unit: | Quality Consultants
Component | Critical Factor | Countermeasure(s)
List of questions | Consultant Availability
List of questions | Long Lead Time
List of questions | Custom Work
Survey Tabulations | Confidentiality
Analysis Report | Consultant Availability
Analysis Report | Custom Work
Recommendations | Consultant Availability
Recommendations | Custom Work
Organizational Unit: | Office Operations
Component | Critical Factor | Countermeasure(s)
List of questions | Long Lead Time
List of questions | Custom Work
Data Collection Form | Supplier Dependent
Data Collection Form | Production Capacity
Survey Tabulations | Computer Failure
Survey Tabulations | Confidentiality
Analysis Report | Production Capacity
Analysis Report | Custom Work
Recommendations | Production Capacity
Recommendations | Custom Work

## Template Crit Fact Spreadsheet
Product: Quality Assessment
Feature/ | Critical Factors
Component
Organization Responsible for Factor
| ✔ | Critial Fator for Feature/Component
| O | Organization with responsibility for factor in at least one checked component

## Template Org Counter Measure
Identify specific countermeasures below for by each organizational unit for each affected critical factor-component.
Organizational Unit:
Component | Critical Factor | Countermeasure(s)
Organizational Unit:
Component | Critical Factor | Countermeasure(s)
Organizational Unit:
Component | Critical Factor | Countermeasure(s)